## Data
What do I measure to enable work flow insights? Where do we start our data journey?
Do | Capture | Enables | Description
1 | Capturing "Work" | Knowing what is being worked on. Visualizing that work. | For each work item there is some way to identify it individuals. Can be as simple as a post-it note with some work title described.
2 | Capture "Completed" Date of Work | Measuring completion rate and forecasting how many similar things can be done in the future. E.g. Throughput or Velocity. | For each work item that has been completed, there is a date that identifies when this occurred captured in the systems managing the data. Can be as simple as a writing the completed date on a post-it note and saving them. E.g. Thoughput or Velocity.
3 | Capture blocked and queued time of work | Identifying and Measuring the impact of impediments and waiting time (constraints). E.g. Process Efficiency | For work items identify how much time that work spend idle through being blocked or because it was waiting for some reason to progress. Could be as simple as adding a dot on a post-it for every day it was idle.
4 | Capture "Type" of work | Measuring completion rate for different types of work and how many similar things of this type can be done in the future. E.g. Bug to Story Ratio. | For each type of work some categoriziation of the work types. For eample, Bugs and Stories. Can be as simple as a different color post-it note.
5 | Capture "Started" Date of Work | Measuring start rate and forecast how many similar things can be started in the future. Mesuring cycle time (how long) work took to complete. E.g. Cycle Time or Time in Process or Age. | For each work item that is started, there is a date that identifies when this occurred in the system managing the data. Can be as simple as writing the start date on a post-it note.
6 | Capture "Arrival" Date of Work | Measuring the arrival rate and forecast how many things arrive in the future. Measuring lead-time (how long) from arriving to completion (versus starting by the team). E.g. Lead Time | For each work item the date it arrived as something that needs to be done is recorded. This might be when a customer submits a ticket or the date the idea first became something considered to do.
7 | Capture "Priority" of Work | Measure completion, started and arrival rates, cycle time and lead-time categorized by work priority. Identify work is started and completed in priority order. | For each work item there is some way to identify the priority of starting that work. Could be as simple as marking each post-it with a High/Medium/Low text.
8 | Capture "Customer Value" of Work | Measure the customer value delivered (not just the rate of work). E.g. Value Delivered | For each work item there is some way to identify the relative or absolute value of delivering that work (as compared to other similar work).
9 | Capture "Cost of Delay" of Work | Measure the incurred cost of unstarted work and identify if addressing constraints makes economic sense. | For each work item there is some way to identify the impact of NOT delivering that work sooner. There isn't really a simple way :)

## Forecasting
What do I measure to enable work flow insights? Where do we start our data journey?
Do | Title | Enables | Description
1 | Capturing "Work" | Knowing what is being worked on. Visualizing that work. | For each work item there is some way to identify it individuals. Can be as simple as a post-it note with some work title described.
2 | Capture "Completed" Date of Work | Measuring completion rate and forecasting how many similar things can be done in the future. E.g. Throughput or Velocity. | For each work item that has been completed, there is a date that identifies when this occurred captured in the systems managing the data. Can be as simple as a writing the completed date on a post-it note and saving them. E.g. Thoughput or Velocity.